## Sheet1
NSA Story Competition ¦ Advanced Planning Calendar
INSERT CHAPTER NAME DATE OF COMPETITION
INSERT CONTACT INFO FOR EVENT PLANNER
Assignee | Task/Topic | October | November | December | January | February | March | April | May | June | July | August | September
SOCIAL AND LOCAL MEDIA
Objective: To identify and employ as many communication channels as possible to market the event locally. Also, to motivate chapter members to spread the information to their circle's of incluence.
Establish Committee and assignments: Social Media, Local Media, Networking
Social Media:
Local Media:
Networking:
PROGRAM AND CONTESTANT SUBMISSIONS/SELECTION
Objective: Develop the compentition rules, judging sheets, speaker slection and event day schedule.
Share competition rules and submission system
Send out solicitation for competitors
Establish selection criteria and committee to choose competitors
Select 10 Finalists
Head shots for marketing and program
Background Bio for program - 2 small paragraphs - 1/2 page on each person
Short Introduction Copy - keep to 2 or 3 sentences. Can't be too long
Produce program for the event - this is a google slide file. Copy and reuse the format
Upload program to web and secure a QR Code for the audience to secure it
Letter to speakers with the program agenda and link to the program for review
EVENT ANNOUNCEMENTS, FACILITY SCHEDULING AND EVENT FOOD
Objective: Make sure the facility is booked and food is ordered for the event. Make sure announcements are sent and storytellers are informed about the event details that they need to know.
Secure day of event and schedule room with location
Communicate with Admin. to make sure event items are covered and ordered
Set up ticketing for members and NON MEMBERS (guests)
JUDGE COMMUNICATION
Objective: Communicate with the judges to make sure they are scheduled and committed. Also that they know what our expectations are for the competition.
Secure Three Judges
Explain rules, judging criteria and event process
COMPETITOR COMMUNCIATION
Objective: Communicate with the competitors about the event. Their position, fornat, rules and event process.
Email selection notification to people chosen
Email people that were not chosen and thank them for entering
Email ST about elements needed for event: Headshot, intro, story background
Committee Members: